## Summary
FORGE AI: delivery summary
Everything on this page is worked out from the Features sheet. Nothing here needs typing.
Overall % done
Features in total
Must-have features done
Features stuck right now
Features by status
Status | Features | Share
Not started
In progress
Being checked
Done
Stuck
Progress by phase
Phase | Features | Done | % done
Phase 1: Accounts and job matching
Phase 2: Resumes, learning and own voice
Phase 3: Interview practice and LinkedIn
Phase 4: Progress tracking and organisations
Phase 5: Launch checks
Progress by area
Area | Features | Done | % done
Accounts and setup
Finding jobs
Resumes and learning
Writing in your own voice
Interview practice
LinkedIn and outreach
Progress tracking
For organisations
Launch checks
Work per developer (screen and backend jobs counted separately)
Developer | Jobs | Done | Under way | Stuck | % done
Developer A
Developer B
Screens vs backend
Side | Jobs | Done | Stuck | % done
Screen work (frontend)
Backend work
Checkpoints
Checkpoint | Tests | Passed | State
Checkpoint 1
Checkpoint 2
Checkpoint 3
Checkpoint 4
Launch
How to use this workbook
1. Features sheet: one row per feature. Change only the yellow columns: Screen status, Backend status and Notes.
2. Statuses: Not started, In progress, Being checked, Done, Stuck (waiting on something), Not needed.
3. Overall, % done, Due and this Summary update themselves. Please do not type over them.
4. Weekly Plan: set each week's Status every Friday after the client demo.
5. Checkpoints: type the measured result; 'Passed?' fills itself in.
6. Example: 'Sign up and log in' with Screen status Done and Backend status Being checked shows Overall = Being checked, 95% done.

## Features
Feature list: every feature in the FORGE AI Product Vision
One row per feature. Read 'What it does' first. Update only the yellow columns; the grey status and % columns work themselves out.
No. | Area | Feature | What it does (for the user) | Screen work to do (frontend) | Backend work to do | Phase | Week | Due | Screen built by | Backend built by | Must have? | What we have today | Waiting on | Screen status | Backend status | Overall | % done | Notes / next step
1 | Accounts and setup | Sign up and log in | People create an account (job seeker, company, university, training institute or staffing firm) and log in safely. | Sign-up and login pages, choose account type, clear error messages | Store passwords securely, keep people logged in, password reset | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer B | Yes | Works, but saves to local files with weak password protection | Where the app will be hosted | Not started | Not started
2 | Accounts and setup | Save everything in a proper database | Everything a user does is saved reliably and is there next time they log in. | Pages read and save through the new database | Set up the database, move existing accounts across | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer B | Yes | Data saved in local files | Which database to use | Not started | Not started
3 | Accounts and setup | Ask permission before using personal data | Users agree to how their data is used before anything is collected. | Permission screen at sign-up, privacy settings page | Record each user's permissions | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer B | Yes | Nothing built yet | Permission wording from client | Not started | Not started
4 | Accounts and setup | Put the app online with backups | The app is reachable on a real web address and data is backed up every day. | — | Deploy to a server, daily backups, alerts if the site goes down | Phase 1: Accounts and job matching | 1 |  | — | Developer B | Yes | Runs only on a developer's computer | Hosting account | Not needed | Not started
5 | Accounts and setup | Fill in your profile | Users enter their role, target role, skills, experience, certifications and LinkedIn link. | Profile form | Save and load the profile | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer B | Yes | Form exists, saved to local files | — | Not started | Not started
6 | Accounts and setup | Upload your resume and photo | Uploading a resume fills in the profile automatically. | Upload button, page to check the filled-in details | Read the resume file and pull out skills, years and job titles | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer A | Yes | Resume reader exists in the recruiter tool | Sample resumes to test with | Not started | Not started
7 | Accounts and setup | Welcome and first steps | New users are guided through their first steps. | Welcome page and checklist | Remember which steps each user has done | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer B | No | Page exists but shows made-up sample data | — | Not started | Not started
8 | Accounts and setup | Home dashboard | Users see their jobs, applications, interviews, profile views and streak at a glance. | Connect the new dashboard design to real numbers | Supply the dashboard numbers | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | Yes | New design done, numbers are made up | — | In progress | Not started
9 | Finding jobs | Collect jobs from company websites | Real jobs are gathered from company career pages. | Show where each job came from | Collect jobs from career pages on a schedule | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer A | Yes | Jobs are made up in code | List of target companies | Not started | Not started
10 | Finding jobs | Collect jobs from LinkedIn, Indeed, Dice and Monster | Jobs from the big job boards appear in the app. | Label each job with its job board | Connect to a licensed job-data provider (copying sites directly breaks their rules) | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer A | Yes | Nothing built yet | Job-data provider account | Not started | Not started
11 | Finding jobs | Add a job by pasting it in | Users can paste any job description they found themselves. | Paste-a-job box | Save the pasted job and analyse it | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer A | Yes | Paste box exists, basic keyword reading | — | Not started | Not started
12 | Finding jobs | Remove duplicate and old jobs | The same job never shows twice, and old jobs are marked. | Show 'posted N days ago' | Spot duplicates across sources, mark old jobs | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
13 | Finding jobs | Search, filter and save jobs | Users search jobs, filter by role, location and seniority, and save or hide them. | Jobs page with search, filters, save and hide | Search with filters | Phase 1: Accounts and job matching | 2 |  | Developer B | Developer A | Yes | Page exists but shows made-up sample data | — | Not started | Not started
14 | Finding jobs | Job alerts | Users get told when a new job matches what they want. | Set up an alert, notification bell | Check new jobs against each alert | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | No | Alert form exists, nothing is sent | — | Not started | Not started
15 | Finding jobs | Read the skills a job needs | The app pulls the required skills out of any job description. | Show required skills on the job page | AI reads the job description; test it against expert-checked examples | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer A | Yes | Simple keyword matching only | Expert-checked job descriptions | Not started | Not started
16 | Finding jobs | Read the certifications and experience a job needs | The app pulls out required certifications, years of experience and seniority. | Requirements panel on the job page | AI pulls out certifications, years and seniority | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer A | Yes | Partly done in the recruiter tool | — | Not started | Not started
17 | Finding jobs | Find the keywords recruiters' software looks for | Users see the words that screening software (ATS) will scan for. | Keyword list, most important first | Rank keywords by importance | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
18 | Finding jobs | Separate must-have skills from nice-to-have | Users see which skills are essential and which are a bonus. | Two groups on the job page | Sort skills into must-have and nice-to-have | Phase 1: Accounts and job matching | 1 |  | Developer B | Developer A | Yes | Done in the recruiter tool | — | Not started | Not started
19 | Finding jobs | Match score for each job | Each job shows a percentage for how well the user fits it. | Match % on job cards and dashboard | Connect the existing FORGE Match scoring to user profiles | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | Yes | Scoring exists in the recruiter tool | — | Not started | Not started
20 | Finding jobs | Readiness for each job | Users see how ready they are for a particular job. | Readiness indicator on each job | Work out readiness per job | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | Yes | Nothing built yet | Agreed readiness formula | Not started | Not started
21 | Finding jobs | Best jobs first | Jobs are ranked so the best opportunities come first. | Top matches list, sort by best opportunity | Score each opportunity (fit, seniority, pay, growth) and rank | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | Yes | Sorted by made-up scores | — | Not started | Not started
22 | Finding jobs | Why this score | Users see which of their skills matched and which are missing. | Matched and missing skills breakdown | Return the reasons with every score | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | Yes | Reasons exist in FORGE Match | — | Not started | Not started
23 | Finding jobs | Skills and roles in demand | Users see which skills and roles employers want most right now. | Trends panel | Count demand across collected jobs | Phase 1: Accounts and job matching | 3 |  | Developer B | Developer A | No | Nothing built yet | Enough collected jobs | Not started | Not started
24 | Finding jobs | Salary ranges | Users see typical pay by role, location and experience. | Salary panel | Work out pay ranges from job data | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | No | Fixed table typed into the code | Salary data in the job feed | Not started | Not started
25 | Resumes and learning | Resume for screening software (ATS) | Users get a resume that passes the software employers use to filter applications. | Resume studio: create screening-friendly version | Write the resume in the user's own voice | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer A | Yes | Template text only | Resume template from client | Not started | Not started
26 | Resumes and learning | Resume for recruiters | Users get a resume written for a human recruiter to read. | Create recruiter version | Write the recruiter version | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
27 | Resumes and learning | Resume for senior roles | Users going for leadership roles get an executive-style resume. | Create executive version | Write the executive version | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
28 | Resumes and learning | Tailor a resume to one job | Each resume can be adjusted to a specific job's keywords. | Pick a job, create a tailored version | Adjust the resume using that job's keywords | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
29 | Resumes and learning | Download as Word or PDF | Users download their resume in either format. | Download buttons | Produce Word and PDF files | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer B | Yes | Nothing built yet | — | Not started | Not started
30 | Resumes and learning | Keep and compare resume versions | Users can look back at, compare and restore earlier versions. | Version list, side-by-side view | Store each version | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer B | No | Counts versions only | — | Not started | Not started
31 | Resumes and learning | Resume score against a job | Users see how well their resume will do for a job, and which keywords are missing. | Score card with missing keywords | Score a resume against a job | Phase 2: Resumes, learning and own voice | 5 |  | Developer B | Developer A | Yes | Nothing built yet | One commercial checker to compare with | Not started | Not started
32 | Resumes and learning | Skills you are missing | Users see the skills they lack for their target role or a job. | Gap page | Find missing skills | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Works on made-up job data | — | Not started | Not started
33 | Resumes and learning | Experience you are missing | Users see the experience they lack. | Experience section on the gap page | Find missing experience | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
34 | Resumes and learning | Certifications you are missing | Users see the certifications worth getting. | Certifications section on the gap page | Find missing certifications | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
35 | Resumes and learning | Most important gaps first | Gaps are marked high, medium or low priority. | Priority labels | Rank the gaps | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Ranking works on made-up data | Expert gap lists to check against | Not started | Not started
36 | Resumes and learning | Today's learning plan | Users see what to learn today. | Today's plan card | Build a daily plan from the gaps | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
37 | Resumes and learning | This week's learning plan | Users see this week's learning plan. | Weekly plan page | Build a weekly plan | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
38 | Resumes and learning | Career roadmap | Users see a long-term path to their target role. | Roadmap timeline | Build the roadmap | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
39 | Resumes and learning | Course suggestions | Users get courses matched to each gap. | Course list with links | Match courses to gaps | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Course names are made up | List of real courses | Not started | Not started
40 | Resumes and learning | Certification plan | Users see which certifications to get, in what order and by when. | Certification plan page | Put certifications in a sensible order | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
41 | Resumes and learning | Learning progress and streaks | Users track progress per skill and keep a learning streak. | Progress bars, streak counter | Save progress | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer B | No | Progress saved, streak is made up | — | Not started | Not started
42 | Resumes and learning | Overall readiness score | Users get one score for how ready they are for their next role. | Readiness ring on the dashboard | Work out the score using the agreed formula | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Based only on how complete the profile is | Agreed readiness formula | Not started | Not started
43 | Writing in your own voice | Learn from your public writing | The app learns how the user writes from their LinkedIn posts, articles and blogs. | Page to add writing samples | Collect and clean the samples | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | Writing samples from pilot users | Not started | Not started
44 | Writing in your own voice | Learn from your private writing | With permission, it also learns from resumes, interview answers and work emails. | Upload private samples | Collect samples only with permission | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
45 | Writing in your own voice | Your voice profile | A summary of how the user sounds when they write. | Profile card | Create the voice profile | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Made-up tags only | — | Not started | Not started
46 | Writing in your own voice | Your communication style | How the user usually structures what they say. | Profile card | Create the style profile | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
47 | Writing in your own voice | Your brand personality | The traits that make up the user's personal brand. | Profile card | Create the brand profile | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
48 | Writing in your own voice | Your professional identity | How the user positions themselves professionally. | Profile card | Create the identity profile | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
49 | Writing in your own voice | Check and correct your profiles | Users can review and fix what the app learned about them. | Edit and save profiles | Keep versions of each profile | Phase 2: Resumes, learning and own voice | 4 |  | Developer B | Developer B | Yes | Nothing built yet | — | Not started | Not started
50 | Writing in your own voice | Resume that tells your career story | Resumes read as one clear career story. | — | Build storytelling into resume writing | Phase 2: Resumes, learning and own voice | 5 |  | — | Developer A | Yes | Nothing built yet | — | Not needed | Not started
51 | Writing in your own voice | Achievements with context | Each achievement says what changed and why it mattered. | — | Rewrite achievements with context | Phase 2: Resumes, learning and own voice | 5 |  | — | Developer A | Yes | Nothing built yet | — | Not needed | Not started
52 | Writing in your own voice | Keep your leadership tone | Senior people keep their leadership voice in what is written. | — | Keep tone consistent with the voice profile | Phase 2: Resumes, learning and own voice | 5 |  | — | Developer A | Yes | Nothing built yet | — | Not needed | Not started
53 | Writing in your own voice | Use your industry's language | Wording fits the user's industry. | — | Use industry-specific wording | Phase 2: Resumes, learning and own voice | 5 |  | — | Developer A | No | Nothing built yet | — | Not needed | Not started
54 | Writing in your own voice | Present you as you really are | The resume positions the user truthfully, in their own terms. | — | Use the identity profile when writing | Phase 2: Resumes, learning and own voice | 5 |  | — | Developer A | No | Nothing built yet | — | Not needed | Not started
55 | Writing in your own voice | Catch text that sounds like AI | Generic, robotic phrasing is flagged before the user sees it. | Warning on flagged text | Detect generic phrasing, check consistency | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
56 | Writing in your own voice | Download or delete your writing samples | Users can take their samples away or delete them for good. | Download and delete buttons | Export and permanently delete samples | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer B | Yes | Nothing built yet | — | Not started | Not started
57 | Writing in your own voice | Prove the voice matching works | Pilot users compare two unlabelled resumes and pick the better one. | Side-by-side comparison page | Record and summarise the choices | Phase 2: Resumes, learning and own voice | 6 |  | Developer B | Developer A | Yes | Nothing built yet | Pilot users' time | Not started | Not started
58 | Interview practice | Practise a production outage | Users handle a realistic system-failure scenario. | Practice screen | Practice engine plus starter scenarios | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Fixed sample scenarios | Scenarios approved by client experts | Not started | Not started
59 | Interview practice | Practise a cloud design challenge | Users design a cloud system under questioning. | Practice screen | Scenarios | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Fixed sample scenarios | Scenarios approved by client experts | Not started | Not started
60 | Interview practice | Practise a leadership situation | Users handle people and decision scenarios. | Practice screen | Scenarios | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Nothing built yet | Scenarios approved by client experts | Not started | Not started
61 | Interview practice | Practise responding to an incident | Users manage a live incident step by step. | Practice screen | Scenarios | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Nothing built yet | Scenarios approved by client experts | Not started | Not started
62 | Interview practice | Practise a technical deep-dive | Users are questioned in depth on their technology. | Practice screen | Scenarios | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Nothing built yet | Scenarios approved by client experts | Not started | Not started
63 | Interview practice | Practise a system design interview | Users answer system design questions. | Practice screen | Scenarios | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Nothing built yet | Scenarios approved by client experts | Not started | Not started
64 | Interview practice | Follow-up questions that react to answers | The interviewer's next question depends on what the user said. | Conversation view | Generate follow-up questions | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
65 | Interview practice | Answer by typing or speaking, against the clock | Practice feels like a real interview. | Text and voice answers, timer, save progress | Turn speech into text, save sessions | Phase 3: Interview practice and LinkedIn | 7 |  | Developer B | Developer B | No | Typed answers only | — | Not started | Not started
66 | Interview practice | Technical depth score | Users see how deep their technical answers were. | Score bar | AI scores answers against a marking guide | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | Yes | Simple rule, not real scoring | Answers scored by experts | Not started | Not started
67 | Interview practice | Communication score | Users see how clearly they communicated. | Score bar | AI scoring | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | Yes | Simple rule, not real scoring | — | Not started | Not started
68 | Interview practice | Leadership score | Users see how they came across as a leader. | Score bar | AI scoring | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | Yes | Simple rule, not real scoring | — | Not started | Not started
69 | Interview practice | Decision-making score | Users see the quality of their decisions. | Score bar | AI scoring | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | Yes | Simple rule, not real scoring | — | Not started | Not started
70 | Interview practice | Interview readiness score | One number for how interview-ready the user is. | Readiness card | Combine the scores | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | Yes | Based on made-up match scores | — | Not started | Not started
71 | Interview practice | Skill-by-skill pass check | Users see which skills are proven and which need work. | Checklist | Set pass marks per skill | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
72 | Interview practice | Feedback and model answers | After each answer, users see what to improve and a strong example. | Feedback panel | Write feedback | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer A | Yes | Nothing built yet | Model answers from experts | Not started | Not started
73 | Interview practice | Improvement over time | Users see their scores improve across sessions. | Trend chart | Keep score history | Phase 3: Interview practice and LinkedIn | 8 |  | Developer B | Developer B | No | Nothing built yet | — | Not started | Not started
74 | LinkedIn and outreach | Thought leadership posts | Users get LinkedIn posts written in their own voice. | Post editor | Write posts using the voice profile | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | One sample post | — | Not started | Not started
75 | LinkedIn and outreach | Technical insight posts | Posts sharing technical know-how. | Post editor | Write posts | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
76 | LinkedIn and outreach | Career story posts | Posts about the user's career experiences. | Post editor | Write posts | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
77 | LinkedIn and outreach | Industry comment posts | Posts commenting on industry news. | Post editor | Write posts | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
78 | LinkedIn and outreach | Keep every post on-brand | All posts sound like the same person. | Consistency indicator | Check each post against the voice profile | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
79 | LinkedIn and outreach | Long technical articles | Users get full-length technical articles. | Article editor | Write articles | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
80 | LinkedIn and outreach | Industry research articles | Research-style articles on the user's field. | Article editor | Write articles | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
81 | LinkedIn and outreach | Opinion articles | Articles giving the user's professional opinion. | Article editor | Write articles | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
82 | LinkedIn and outreach | Executive articles | Articles for senior leaders. | Article editor | Write articles | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
83 | LinkedIn and outreach | What to post and why | Users get a content plan and a positioning strategy. | Strategy page | Create the plan | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
84 | LinkedIn and outreach | Content calendar | Users plan and schedule their posts. | Calendar page | Scheduling and reminders | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer B | Yes | List of scheduled posts only | — | Not started | Not started
85 | LinkedIn and outreach | Post to LinkedIn | Posts go to LinkedIn directly, or the user gets a reminder to post by hand. | Post / copy-to-LinkedIn button | Connect to LinkedIn once access is approved | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer B | No | Nothing built yet | LinkedIn access approval | Not started | Not started
86 | LinkedIn and outreach | Messages to recruiters | Users get messages to recruiters in their own voice. | Message writer | Write messages | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | One sample draft | — | Not started | Not started
87 | LinkedIn and outreach | Referral requests | Users get messages asking contacts for referrals. | Message writer | Write messages | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
88 | LinkedIn and outreach | Networking messages | Users get messages for building their network. | Message writer | Write messages | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
89 | LinkedIn and outreach | Follow-up reminders | Users are reminded to follow up at the right time. | Reminder list | Schedule follow-ups | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer B | Yes | Nothing built yet | — | Not started | Not started
90 | LinkedIn and outreach | See who replied | Users track replies to their outreach. | Campaign board | Save campaigns and replies | Phase 3: Interview practice and LinkedIn | 9 |  | Developer B | Developer B | No | Made-up sample campaigns | — | Not started | Not started
91 | Progress tracking | Track applications through to offers | Users track every application: applied, interview, offer. | Application board | Save each application's stage | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer B | Yes | Stages are saved | — | Not started | Not started
92 | Progress tracking | Career progress | Users see their progress towards their target role. | Progress timeline | Work out progress | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
93 | Progress tracking | Interview results over time | Users see how their interview scores are changing. | Charts | Combine interview results | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
94 | Progress tracking | How many applications turn into interviews and offers | Users see their success rate at each stage. | Funnel chart | Calculate the rates | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Calculated on made-up data | — | Not started | Not started
95 | Progress tracking | Readiness over time | Users see their readiness score history. | History chart | Save score snapshots | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
96 | Progress tracking | Is my LinkedIn activity working | Users see whether their posts are raising their visibility. | LinkedIn results panel | Track results (typed in by hand until LinkedIn access is approved) | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | No | Random made-up figures | LinkedIn access approval | Not started | Not started
97 | Progress tracking | Progress dashboard | One page showing all of the user's progress. | Progress dashboard | Summarise progress | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
98 | Progress tracking | What to do next | Users get suggestions for improving their chances. | Suggestions list | Create suggestions | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Fixed text | — | Not started | Not started
99 | Progress tracking | Technology trends | Users see which technologies are rising or fading. | Trends page | Analyse trends in job data | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
100 | Progress tracking | Roles to aim for next | Users get suggested next roles. | Suggestions | Suggest roles | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | Yes | Fixed table | — | Not started | Not started
101 | Progress tracking | Which certifications are worth it | Users see which certifications employers value. | Guidance panel | Base guidance on job demand | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
102 | Progress tracking | Market reports | Users get a regular report on their job market. | Report page and download | Create the report | Phase 4: Progress tracking and organisations | 10 |  | Developer B | Developer A | No | Nothing built yet | — | Not started | Not started
103 | For organisations | Each organisation's data kept separate | No organisation can ever see another's people or data. | Organisation switcher | Keep every organisation's data apart, with tests to prove it | Phase 4: Progress tracking and organisations | 11 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
104 | For organisations | Manage people, groups and programs | Admins add people (one by one or from a spreadsheet) and put them in groups. | Admin pages, spreadsheet upload | Manage seats and groups | Phase 4: Progress tracking and organisations | 11 |  | Developer B | Developer B | Yes | Nothing built yet | Pilot client's user list | Not started | Not started
105 | For organisations | Group progress dashboard | Universities, institutes and company training teams see how their group is doing. | Group dashboard, download as spreadsheet | Combine figures for the group | Phase 4: Progress tracking and organisations | 11 |  | Developer B | Developer A | Yes | Nothing built yet | — | Not started | Not started
106 | For organisations | Staffing firm tools | Staffing firms match their candidates to client job requests. | Job request and shortlist pages | Reuse the recruiter tool's matching | Phase 4: Progress tracking and organisations | 11 |  | Developer B | Developer A | No | Recruiter email tool exists | — | Not started | Not started
107 | For organisations | Connect to other company systems | Organisations connect their hiring, HR and training systems. | Connection settings page | Connection points for other systems | Phase 4: Progress tracking and organisations | 12 |  | Developer B | Developer A | No | Nothing built yet | The first client's systems | Not started | Not started
108 | For organisations | Admins and members see different things | Each person only sees what their role allows. | Menus change with role | Check permissions on every action | Phase 4: Progress tracking and organisations | 12 |  | Developer B | Developer B | Yes | Only recruiter vs job seeker split | — | Not started | Not started
109 | For organisations | Pay for individual programs | Individuals buy Resume Optimization, Interview Readiness or Career Accelerator. | Plans and checkout | Connect a payment provider | Phase 4: Progress tracking and organisations | 12 |  | Developer B | Developer B | Yes | Nothing built yet | Payment provider account | Not started | Not started
110 | For organisations | Organisation licences | Organisations buy licences, training programs and platform access. | Licence page | Licence records and invoices | Phase 4: Progress tracking and organisations | 12 |  | Developer B | Developer B | No | Nothing built yet | Agreed pricing | Not started | Not started
111 | For organisations | Book a coaching session | Users book coaching sessions included in their program. | Booking calendar | Save bookings, send reminders | Phase 4: Progress tracking and organisations | 12 |  | Developer B | Developer B | No | Nothing built yet | Coaches' availability | Not started | Not started
112 | Launch checks | Download or delete all your data | Any user can download everything or delete their account completely. | Buttons in settings | Export and permanently delete across the whole system | Phase 5: Launch checks | 13 |  | Developer B | Developer B | Yes | Nothing built yet | — | Not started | Not started
113 | Launch checks | Security check and fixes | No serious security problems at launch. | — | Fix what the security check finds | Phase 5: Launch checks | 13 |  | — | Developer B | Yes | Nothing built yet | Security reviewer booked | Not needed | Not started
114 | Launch checks | Handles many users at once | The app stays fast with 100 people using it at the same time. | Speed up slow pages | Load test and speed fixes | Phase 5: Launch checks | 13 |  | Developer B | Developer B | Yes | Nothing built yet | — | Not started | Not started
115 | Launch checks | Accuracy and running-cost check | Every AI feature is re-tested, and the AI cost per user fits the price. | — | Re-run accuracy tests, reuse earlier results to save cost | Phase 5: Launch checks | 13 |  | — | Developer A | Yes | Result reuse exists for email checks | — | Not needed | Not started
116 | Launch checks | Pilot test and go live | Pilot users try everything, problems are fixed, then launch. | Fix screen problems | Fix backend problems | Phase 5: Launch checks | 13 |  | Developer B | Developer A | Yes | Nothing built yet | Pilot users | Not started | Not started

## Weekly Plan
Weekly plan: 2 developers, 13 weeks
What each developer delivers each week. Developer A builds the engines behind the screens; Developer B builds the screens and the platform. Every Friday: join the work up and show the client.
Week | Starts | Phase | Developer A delivers (engines) | Developer B delivers (screens and platform) | Checkpoint / milestone | Status | Features due | Features done | Notes
1 |  | Phase 1: Accounts and job matching | Read skills, certifications, experience and keywords from job descriptions; testing kit to measure accuracy | Database; secure sign-up and login for all account types; permission screen; put the app online | — | Not started
2 |  | Phase 1: Accounts and job matching | Collect jobs (company sites, job-board feed, pasted jobs); remove duplicates; read uploaded resumes | Profile page; resume and photo upload; jobs page with search, filters, save and alerts | — | Not started
3 |  | Phase 1: Accounts and job matching | Match score, readiness and ranking for every job, with reasons; skills in demand | Home dashboard on real numbers; top matches; alert notifications; welcome steps | Checkpoint 1 | Not started
4 |  | Phase 2: Resumes, learning and own voice | Learn each user's writing voice (4 profiles); find missing skills, experience and certifications | Writing-sample upload with permission; profile review page; gaps page | — | Not started
5 |  | Phase 2: Resumes, learning and own voice | Write three resume types in the user's voice; tailor to a job; resume score | Resume studio: create, compare, keep versions, download Word or PDF | — | Not started
6 |  | Phase 2: Resumes, learning and own voice | Learning plans, roadmap, courses, certification plan; overall readiness; catch AI-sounding text | Learning page with progress and streaks; readiness ring; download or delete writing samples | Checkpoint 2 | Not started
7 |  | Phase 3: Interview practice and LinkedIn | Interview practice engine: 6 scenario types, follow-up questions, 12 starter scenarios | Practice screen: type or speak answers, timer, save sessions | — | Not started
8 |  | Phase 3: Interview practice and LinkedIn | Scores for technical depth, communication, leadership and decisions; feedback and model answers | Results page; improvement over time | — | Not started
9 |  | Phase 3: Interview practice and LinkedIn | LinkedIn posts and articles in the user's voice; content plan; outreach messages | Content calendar; outreach campaigns, follow-up reminders, replies | Checkpoint 3 | Not started
10 |  | Phase 4: Progress tracking and organisations | Progress, interview and success-rate figures; technology trends, next roles, certification advice, salaries | Progress dashboard; application board; trends page | — | Not started
11 |  | Phase 4: Progress tracking and organisations | Keep each organisation's data separate; staffing firm matching; group figures | Admin pages (people, groups, spreadsheet upload); group dashboard | — | Not started
12 |  | Phase 4: Progress tracking and organisations | Connection points for other company systems | Payments for programs and licences; coaching booking; admin vs member access | Checkpoint 4 | Not started
13 |  | Phase 5: Launch checks | Re-test accuracy; check AI cost per user | Security fixes; download/delete all data; speed test with 100 users; backups | Launch (8 Jan 2027 if the team takes the year-end break) | Not started

## Checkpoints
Checkpoints: what must be true before moving to the next phase
Type the measured number in the yellow 'Result we got' column. 'Passed?' fills itself in. Targets (blue) are from the 13-week plan.
Checkpoint | Week | Date | What we measure | Target | Need | Result we got | Passed? | Who measures it
Checkpoint 1 | 3 |  | Share of required skills the app finds in job descriptions (vs experts) | 90% | at least |  |  | Developer A + experts
Checkpoint 1 | 3 |  | Share of test candidates where experts agree with the top 3 jobs | 80% | at least |  |  | Client experts
Checkpoint 1 | 3 |  | Pilot users signed up | 10 | at least |  |  | Project lead
Checkpoint 2 | 6 |  | Share of generated resumes that pass the screening-software check | 90% | at least |  |  | Developer A
Checkpoint 2 | 6 |  | Share of pilot users who prefer the own-voice resume (blind test) | 70% | at least |  |  | Pilot users
Checkpoint 3 | 9 |  | Interview scenarios approved by client experts | 12 | at least |  |  | Client experts
Checkpoint 3 | 9 |  | Share of answers where the app's score is within 1 point of the expert's | 80% | at least |  |  | Developer A + experts
Checkpoint 4 | 12 |  | Organisations live with a group of users | 1 | at least |  |  | Developer B
Checkpoint 4 | 12 |  | Times one organisation could see another's data in tests | 0 | at most |  |  | Developer A
Launch | 13 |  | Serious security problems still open | 0 | at most |  |  | Security reviewer
Launch | 13 |  | People using the app at once without slowdown | 100 | at least |  |  | Developer B
Percentages: type 0.85 for 85%.

## Glossary
Glossary
Plain meanings for the few technical words used in this workbook.
Term | What it means
Screen work (frontend) | Everything the user sees and clicks: pages, buttons, forms, charts.
Backend work | The work behind the screens: saving data, AI, calculations, connecting to other services.
Developer A | Builds the engines behind the screens: job collection, matching, AI writing, scoring, analytics.
Developer B | Builds the screens and the platform: pages, logins, database, payments, admin, hosting.
ATS (applicant tracking system) | Software employers use to filter resumes automatically before a person reads them.
Job description | The text of a job advert: duties, required skills, experience.
FORGE Match | FORGE AI's scoring that gives each job a match percentage for a candidate. Already built for the recruiter tool.
Voice profile | What the app learns about how a person writes, so generated text sounds like them, not like generic AI.
Checkpoint | A measured test at the end of each phase. The next phase starts only when it passes.
Pilot users | Real early users who try the app and give feedback before launch.
Licensed job-data provider | A paid service that legally supplies job listings from boards like LinkedIn and Indeed.
Group (cohort) | A batch of people an organisation enrols together, for example one university class.
Must have? | Yes = needed for launch. No = valuable, but can follow shortly after if time runs out.
% done | Worked out from the two statuses: In progress counts as 50%, Being checked 90%, Done 100%.

## Settings
Settings
Options used by the dropdowns and dates on the other sheets. Change the start date here and every due date moves.
Setting | Value | Status | Counts as finished | Who | Must have? | Phase
Project start date (Monday of week 1) | 2026-10-05 | Not started | 0% | Developer A | Yes | Phase 1: Accounts and job matching
|  | In progress | 50% | Developer B | No | Phase 2: Resumes, learning and own voice
|  | Being checked | 90% | Both |  | Phase 3: Interview practice and LinkedIn
|  | Done | 100% |  |  | Phase 4: Progress tracking and organisations
|  | Stuck | 0% |  |  | Phase 5: Launch checks
Not needed
'Not needed' means the feature has no screen work (or no backend work), so it is left out of the % done.
Note on B5: From the FORGE AI 2-Developer 13-Week Plan. Change it and all due dates update.